## Main Schedule
Topic | Date Complete | PIC | Duration (day) | Status
Discussion and Kickoff | 2025-01-20 | Nguyễn Nhật Huy | 5 days
Finalize requirements, scope, and technology stack | 2025-01-14 | Nguyễn Nhật Huy | 1 day
Set up project repository, CI/CD pipeline | 2025-01-15 | Nguyễn Xuân Hoài | 1 day
Basic project structure | 2025-01-16 | Lê Quang Hưng | 1 day
Assign roles and create development timeline | 2025-01-17 | Trần Trung Vũ | 1 day
Approved project plan | 2025-01-20 | Trần Phước Tuấn | 1 day
Start Development: Multi-Email Integration | 2025-01-27 | Nguyễn Xuân Hoài | 5 days
Set up secure email integration | 2025-01-21 | Nguyễn Xuân Hoài | 1 day
Create APIs for email accounts | 2025-01-22 | Nguyễn Xuân Hoài | 1 day
Build UI for email accounts | 2025-01-23 | Lê Quang Hưng | 1 day
Functional email integration | 2025-01-24 | Lê Quang Hưng | 1 day
Milestone 1: Multi-Email Integration and Initial Template System | 2025-02-03 | Lê Quang Hưng | 5 days
Finalize testing for multi-account management | 2025-01-28 | Lê Quang Hưng | 1 day
Develop template creation and editing | 2025-01-29 | Trần Trung Vũ | 1 day
Dynamic placeholder support | 2025-01-30 | Trần Trung Vũ | 1 day
Save and reuse templates | 2025-01-31 | Trần Phước Tuấn | 1 day
Fully tested multi-email integration | 2025-02-03 | Trần Phước Tuấn | 1 day
Custom Group Management (Phase 1) | 2025-02-10 | Trần Trung Vũ | 5 days
Define group properties | 2025-02-04 | Trần Trung Vũ | 1 day
API endpoints for group management | 2025-02-05 | Trần Trung Vũ | 1 day
UI for managing groups | 2025-02-06 | Trần Phước Tuấn | 1 day
Backend and frontend for group management | 2025-02-07 | Trần Phước Tuấn | 1 day
Excel File Import for Group Management (Phase 1) | 2025-02-17 | Trần Phước Tuấn | 5 days
Backend to parse Excel files | 2025-02-11 | Trần Phước Tuấn | 1 day
Frontend interface for uploading files | 2025-02-12 | Trần Phước Tuấn | 1 day
Auto-mapping for common columns | 2025-02-13 | Nguyễn Nhật Huy | 1 day
Manual column mapping | 2025-02-14 | Nguyễn Nhật Huy | 1 day
Excel file import with column mapping | 2025-02-17 | Nguyễn Nhật Huy | 1 day
Milestone 2: Full Custom Group Management and Property-Based Personalization | 2025-02-24 | Nguyễn Nhật Huy | 5 days
Integrate Excel import into group management | 2025-02-18 | Nguyễn Nhật Huy | 1 day
Add data validation for duplicates | 2025-02-19 | Nguyễn Xuân Hoài | 1 day
Link group properties with email templates | 2025-02-20 | Nguyễn Xuân Hoài | 1 day
Backend for personalized email generation | 2025-02-21 | Lê Quang Hưng | 1 day
Frontend to preview personalized emails | 2025-02-24 | Lê Quang Hưng | 1 day
Recurring Email Actions | 2025-03-03 | Nguyễn Xuân Hoài | 5 days
Implement scheduling logic | 2025-02-25 | Nguyễn Xuân Hoài | 1 day
Store recurring email configurations | 2025-02-26 | Nguyễn Xuân Hoài | 1 day
UI for setting up recurring emails | 2025-02-27 | Lê Quang Hưng | 1 day
Integrate with background job processors | 2025-02-28 | Lê Quang Hưng | 1 day
Tested recurring email scheduling | 2025-03-03 | Lê Quang Hưng | 1 day
Milestone 3: Insights and Conditional Logic in Templates | 2025-03-10 | Lê Quang Hưng | 5 days
Track email performance metrics | 2025-03-04 | Trần Trung Vũ | 1 day
Create backend APIs for metrics retrieval | 2025-03-05 | Trần Trung Vũ | 1 day
Build UI for displaying analytics | 2025-03-06 | Trần Phước Tuấn | 1 day
Enable conditional sections in templates | 2025-03-07 | Trần Phước Tuấn | 1 day
Build UI for creating conditions in templates | 2025-03-10 | Trần Phước Tuấn | 1 day
Final Testing and Deployment | 2025-03-17 | Trần Trung Vũ | 5 days
Comprehensive testing of all features | 2025-03-11 | Trần Trung Vũ | 1 day
Fix bugs and optimize performance | 2025-03-12 | Trần Trung Vũ | 1 day
Prepare documentation for deployment | 2025-03-13 | Trần Phước Tuấn | 1 day
User and technical documentation | 2025-03-14 | Trần Phước Tuấn | 1 day
Project deployed to staging/production | 2025-03-17 | Trần Phước Tuấn | 1 day