## mailcrafter - mvc
MailCrafter - MVC
This board is where the team will manage their day-to-day sprint tasks. Each task is connected to the epic from the roadmap. Use the different views to plan your next sprint as well as see your current sprint progress.
Week 2 - Account Management
Name | Sub Tasks | Owner | Status | Priority | Type | Role | Task Description | Deadline
Requirements & Design | Use case diagrams,Functional Requirements,Nonfunctional Requirements | Mingo Nguyen | In Progress | High | Document | Design | User Login tài khoản. Màn Home -> ở mục quản lí account, cho phép user quản lí nhiều emails. (Thêm/Xóa Email) | 2025-01-16
Subitems | Name | Owner | Status | Subtask Description
Use case diagrams
Functional Requirements
Nonfunctional Requirements
User Login | UI - Login Screen,Register Account,Logic - Database | vutt1808@gmail.com | In Progress | High | Feature | Dev | User Login thành công sẽ chuyển về trang Home. User chưa có account thì đăng ký
Subitems | Name | Owner | Status | Subtask Description
UI - Login Screen
Register Account
Logic - Database
Add Email Account | UI,Verify Account,Save to DB | Mingo Nguyen | Ready to start | High | Feature | Dev |  | 2025-01-20
Subitems | Name | Owner | Status | Subtask Description
| UI |  |  | Có nút Add Acccount, yêu cầu user nhập email+pass
| Verify Account |  |  | Lưu các thông tin của Account vào database nếu user nhập đúng email và pass
| Save to DB |  |  | Save to DB, link emails account to User Account
Delete Email Account | UI,Delete From DB |  | Ready to start | High | Feature | Dev
Subitems | Name | Owner | Status | Subtask Description
UI
Delete From DB
View Email Account | UI,Display All Email Accounts attached to the User | HungLe | Ready to start | High | Feature | Dev
Subitems | Name | Owner | Status | Subtask Description
UI
Display All Email Accounts attached to the User
2025-01-16 to 2025-01-20
Week 3 - {}
Name | Sub Tasks | Owner | Status | Priority | Type | Role | Task Description | Deadline
DEV
DEV
Week 3
Name | Sub Tasks | Owner | Status | Priority | Type | Role | Task Description | Deadline
Week 3
Name | Sub Tasks | Owner | Status | Priority | Type | Role | Task Description | Deadline
Sprint 1
Name | Sub Tasks | Owner | Status | Priority | Type | Role | Task Description | Deadline
Open a monday account |  |  | Done | Critical | Feature | Dev
Install from a template |  |  | Done | High | Document | Dev
Backlog
Name | Sub Tasks | Owner | Status | Priority | Type | Role | Task Description | Deadline
Change themes |  |  | Backlog | Best Effort | Improvement | Dev